## Sheet1
Production Build Readiness Checklist
Not sure if your product is “Production Build Ready”? This handy checklist provides useful information to confirm you have completed all the preliminary steps and tasks. You can complete it on your own or as a joint exercise with a Simplexity NPI team member.
| Product Build Planning | Notes
FALSE | Define build objectives and create a plan for unit quantities and allocations | Download: Project Build Plan Template
Engineering Requirements and Planning
FALSE | Define system and component specifications that are critical to product function (Simplexity uses “Critical Performance Metrics”) | Download: PRD Template
FALSE | Complete collaborative Design Reviews for Manufacturing, Assembly, Service, Test, and Quality on all assemblies
FALSE | Develop an assembly plan including subassembly build and testing instructions and acceptance criteria
FALSE | Review test results and issues to ensure root causes are well understood
FALSE | Complete First Article Inspections and component dispositions
FALSE | Complete a pre-build risk assessment | Risk Analysis Template Webpage
Build Management
FALSE | Enable configuration management (unit traveler, serial numbers, configurations, rework status)
FALSE | Implement and complete training for issue tracking system
FALSE | Create assembly instructions with stakeholder review and approval
FALSE | Implement revision control management for units and sub-assemblies
FALSE | Plan and prepare physical build space, lockable Inventory space, and non-conforming material storage areas
FALSE | Create a resource plan and allocate and train resources to ensure adequate support for build schedule
Product Quality Plan Development
FALSE | Write and approve product risk management plan
FALSE | Create a Verification & Validation Test plan and write test protocols
FALSE | Define Incoming inspection procedures
FALSE | Design, build, and validate In-line and end-of-line assembly and test fixtures
FALSE | Define data collection requirements and methods
FALSE | Create product build corrective action plans
Contract Manufacturing & Other Vendor Selection
FALSE | Document your requirements, including capabilities, capacity, and quality assurance expectations so CM can confirm “fit” | Download: Project Information Sheet for CMs Template
FALSE | Develop a pool of potential vendors
FALSE | Send out CM Capability Assessment Survey to vendor prospects | Download: CM Capability Assessment Survey
FALSE | Complete initial and then detailed qualification
FALSE | Prepare CM RFQ Package | Download: CM RFQ Package Template
FALSE | Select vendors and create a contract
Need Help?
Contact us no matter where you are in developing your new product or within any stage of the product development process. Our engineers will be happy to help you navigate any phase of bringing your innovation to production – from early development to transfer to manufacturing.
email: info@simplexitypd.com |  | web: simplexitypd.com
Production Build Readiness Checklist ¦ Copyright © 2024 Simplexity Product Development