## Product Development Build Plan
Product Build Planning Template
INSTRUCTIONS: Copy the template below and customize to match your project. You can combine or separate the manufacturing levels into different disciplines if preferred. Change the naming and add/remove build columns to match your preferred nomenclature. Continue to update as project progresses. As this document is refined over time and more detailed information is developed for each phase, links can be added to the template for greater versatility. Feel free to delete the "explanation" column after setting up the table.
| Category | Explanation | Ph 2A Pre-Proto | Ph 2B Proto 1 | Ph 2C Proto 2 | Ph 3A Pre-Production | Production
| Build Objective | List objective of the build. For example: • Review form and fit of parts, no functional testing. Present at trade show. • Full assemblies with skins are not needed. • Build pre-production units for design verification test (DVT)
| Build Qty | List expected quantities. If multiple lots of a build are expected and have different objectives, list in separate columns.
| Build Location | Simplexity (identify which division), client site, tooling vendor site, or CM. Consider infrastructure requirements such as power, air, vacuum, clean room.
| Manufacturing level, ME | List the expected manufacturing process to be used. For example, 1. Pre-Proto/ Breadboard: mechanical 3D printed components 2. Low Volume Prototype: mechanical machined components 3. High Volume Production: mechanical cast or injection molded components
| Manufacturing level, EE & SW/FW | List the expected manufacturing process to be used. For example, 1. Pre-Proto/ Breadboard: a. Electrical development kit bread boarding b. FW/SW test scripts 2. Low Volume Prototype: a. Electrical non-form factor board b. FW/SW with core functionality 3. High Volume Production: a. Electrical production board b. FW/SW full featured production code
| Parts procurement | Identify who is responsible for parts procurement
| Factory Readiness | List the expected labor, equipment, parts to be in place for the manufacturing process. For example, 1. Pre-Proto/ Breadboard: a. Skilled technician or engineer labor b. Hand tools/ Lab tools c. Pre-Prototype parts, 3D printed parts 2. Low volume Prototype a. Skilled technician or engineer labor b. Lab tools, Automated equipment as appropriate c. Prototype parts 3. High Volume Production a. CM operator labor, CM process engineering b. Validated tools and assembly fixtures c. Production parts
| Build Tools/ Fixtures | 1. Identify tools & fixtures required for each build and level of validation required. 2. Identify who is responsible for developing tools/ fixtures.
| Design Control | Identify if under Change Control, if applicable
| Design Configuration | Identify any differences in design configurations for each build
| Image Reference or Link | Insert a small screen shot of the assembly or a link to a descriptive confluence page.
| NPI Objectives | 1. Identify planning processes needed, such as supplier selection and engagement level. 2. Identify if NPI transfer or transfer to client is expected for the build 3. Identify level of documentation package expected
| Design Objectives | 1. Identify design stability required (ex. major or minor changes anticipated, change control implemented) 2. Identify types of reviews needed (ex. design reviews, FMEA, DFM analysis)
| Test Objectives | 1. Summarize tests to be run, including regulatory if needed. Link to test plan(s). 2. Identify test objective (ex. ECT for Phase 2 protos, DVT for Phase 3)
| Quality Objectives | 1. Identify part inspection quality goals (ex. Form/Fit/Function, FAI, CpK) 2. Identify system or subsystem quality goals (ex. Critical Performance Measures, CpK, First Pass Yield). 3. Identify if CPMs are identified, verified, and if there is a Process capability (Cpk) or First pass yield (FPY) target.
Need Help?
Contact us no matter where you are in developing your new product or within any stage of the product development process. Our engineers will be happy to help you navigate any phase of bringing your innovation to production – from early development to transfer to manufacturing.
email: info@simplexitypd.com | [6 empty] | web: simplexitypd.com
Product Build Planning Template ¦ Copyright © 2024 Simplexity Product Development